## Project Profit Plan
|  |  | Project A Contract Valuation Section III - Project Profit Plan | [6 empty] | Project Ref | 12345
[10 empty] | Review Date | 2021-08-16
[10 empty] | Report Period | 2022-07-21
[10 empty] | Region | ACA Central
[10 empty] | Progress Claim | 7
[10 empty] | Forecast Type | Monthly Forecast
|  |  | Current |  | BTW Delta |  |  | BTW Forecast at Completion
| Item | Original Budget | FAC | Contingency in FAC | Best | Target | Worst | Best | Target | Worst | Comments
1 | Initial Contract | [6 empty] | 553842 | 553842 | 553842
2 | Approved Variations | - | 22991 |  |  |  |  | 22991 | 22991 | 22991
3 | Approved Claims | - | - |  |  |  |  | - | - | -
4 | SoR Quantity Adjustment | - | - | [6 empty] | -
5 | Provisional Sum | - |  |  | 218 | 500 | 187 | 1066 | 1052 | 1035 | PS works scheduled to start newt month
6 | Rise and Fall | - | - |  |  |  |  | - | - | -
7 | Incentive Payment |  | 2418 |  | 108 | 98 |  | 2526 | 2516 | 2418 | Tracking tow ards 80X achievement
8 | KRA | - | - |  |  |  |  | - | - | -
9 | KPIs | - | - |  |  |  |  | - | - | -
10 | Share of Cost Savings | - | - | [6 empty] | -
| Sub Total - Approved Income | 0 | 25409 |  | 0 | 0 | 0 | 0 | 0 | 0
11 | Unapproved Variations (Valued) | - | - |  | 846 | 500 |  | 846 | 500 | - | Clent verbally approved 500k, negotiations continuing
12 | Unapproved Claims (Valued) | - | [5 empty] | - | - | -
| Sub Total - Unapproved Income | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal - Approved + Unapproved | 0 | 25409 |  | 0 | 0 | 0 | 0 | 0 | 0
13 | Adjustment lor Under I Over Cairns | - | - |  | - | - | - | - | - | -
| PROJECT REVENUE | 0 | 25409 |  | 0 | 0 | 0 | 0 | 0 | 0
14 | Other Income-Insurance Recoveries | - | - |  |  |  |  | - | - | -
15 | Other Income-Outside Head Contract | - | - |  |  |  |  | - | - | -
| TOTAL REVENUE | 0 | 25409 |  | 0 | 0 | 0 | 0 | 0 | 0
COST AND CONTNGENCY
16 | Recurring Indirect Cost | 110386 | 99895 | 750 |  |  |  | 99895 | 99895 | 99895 | Northern compound closure 3 months early
17 | Non Recurring Indirect Cost | [6 empty] | - | - | -
18 | Direct Cost | 335022 | 364295 | 1500 |  |  |  | 364295 | 364295 | 364295 | EW 500k poductivity, 1m revised commissioning strategy
| Subtotal Cost | 0 | 0 | 0 | - | - | - | 0 | 0 | 0
19 | Finance Contingencies |  | - | - |  |  |  | - | - | -
20 | Design Growth | 4296 | 1298 | 1298 | 1298 | 2000 | - |  | -702 | 1298 | 5/55 packages reman not at IFC
21 | Unallocated Contingencies | 34583 | 37450 | 37450 | 18725 | 9362 | 3500 | 18725 | 28067 | 33950
22 | Escalation |  | 5140 | 5140 | 2500 | - | 500 | 2640 | 5140 | 5640 | Structures procurement ongoing
23 | Risk & Opportunities | 2014 | 6014 | 6014 | 2000 | - | 2000 | 4014 | 6014 | 8014 | Algned to R&O register
24 | Inclement Weather | 3723 | 2723 | 2723 | - | 500 | 1000 | 2723 | 3223 | 3723 | Approaching wet season
| Contingencies | 44616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Additional revenue coverd by 250k additional cost
25 | Additional Costs lor Unapproved Income |  | - | - | 250 | 250 |  | 250 | 250 | -
| TOTAL PROJECT COST | 44616 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| % OF FORECAST |  |  | 0% | 0% | 0% | 0%
FINANCIAL STATUS
| Gross Profit Marain ($) | -44616 | 25409 |  |  |  |  | 0 | 0 | 0
| Gross Profit Margin (X) | #DIV/0! | 100% |  |  |  |  | 0% | 0% | 0%
| Previous Gross Profit Margin ($) |  | -19207 |  |  |  |  | 0 | 0 | 0
| Previous Gross Profit Margin (X) |  | -75.59% |  |  |  |  | 0% | 0% | 0%
| Movement from lost Period |  | 44616 |  |  |  |  | 0 | 0 | 0